## Project Plan
Explainable AI ¦ Project Plan & Deliverables
Breast cancer (GSE96058) only • October 2026 – June 2027 • Planned dates subject to university confirmation
ID | Work package | Contributors | Start | Finish | Depends on | Expected evidence / deliverable | Status
T01 | Scope, requirements and risk plan | Ziad + Gamal | 2026-10-12 | 2026-10-26 |  | Approved consolidated breast-only specification and risk assessment | Prepared
T02 | Literature review, DOI checks and final formatting | Gamal + Ziad | 2026-10-12 | 2026-10-26 |  | Verified breast cancer literature review with linked references | Prepared
T03 | Dataset acquisition, labels and replicate audit | Mostafa + Mohamed | 2026-10-16 | 2026-11-10 |  | GSE96058 matched primary-sample IDs, labels and 136 replicate audit | In progress / verify
T04 | Defense I materials, repository and rehearsal | All four | 2026-10-20 | 2026-10-27 | T01,T02 | Submission materials, initial EDA, GitHub evidence, presentation | Pending review
T05 | Expression scale, PAM50 alias and EDA verification | Mostafa + Ziad | 2026-10-27 | 2026-11-18 | T03 | Verify log2(FPKM+0.1), gene IDs, documented ORC6L to ORC6 alias, class balance | In progress / verify
T06 | Reproducible split and evaluation protocol | Ziad + Mohamed | 2026-11-10 | 2026-11-25 | T03 | Group-safe 80/20 holdout proposal and train-only CV pipeline | Planned
T07 | Initial PAM50-gene baselines | Gamal + Mostafa | 2026-11-20 | 2026-12-14 | T05,T06 | LR/SVM baseline, initial five-class metrics, record Normal-like issues | Planned
T08 | Initial thesis and Defense II experiments | All four | 2026-12-01 | 2026-12-22 | T07 | Initial thesis Dec 15; Defense II Dec 22; reproducible baseline evidence | Planned
T09 | Advisor feedback and revised thesis | All four | 2026-12-23 | 2026-12-29 | T08 | Incorporate Defense II recommendations in revised thesis | Planned
T10 | Compare PAM50 and ANOVA-selected genes | Mostafa + Gamal | 2026-12-30 | 2027-02-10 | T06,T07 | Training-fold ANOVA subset-size selection and PAM50 baseline comparison | Planned
T11 | Compare L1 / elastic-net-selected genes | Ziad + Mohamed | 2027-01-05 | 2027-02-15 | T06,T07 | Sparse gene panels fitted only on training folds | Planned
T12 | Compare LR, SVM, RF and XGBoost | All four | 2027-02-01 | 2027-03-01 | T10,T11 | Consistent CV macro-F1 and per-class comparisons | Planned
T13 | First Streamlit UI and input validation | Mohamed + Ziad | 2027-01-20 | 2027-03-10 | T05 | Single/batch expression upload; exact schema; friendly error messages | Planned
T14 | Curated gene biology evidence and references | Gamal + Mohamed | 2027-01-25 | 2027-04-10 | T02 | Verified gene-breast subtype context with DOI/PMID and limitations | Planned
T15 | Select final breast model; untouched test evaluation | Ziad + Mostafa | 2027-03-02 | 2027-03-15 | T12 | Locked pipeline; final 5-class decision; held-out metrics and calibration review | Planned
T16 | SHAP explanations and reliability checks | Gamal + Ziad | 2027-03-02 | 2027-04-12 | T12 | Class-specific SHAP, faithfulness, stability and interpretation | Planned
T17 | Defense III model and prototype demonstration | All four | 2027-03-05 | 2027-03-16 | T13,T15 | Mar 16: current reproducible modeling results and app demonstration | Planned
T18 | Application integration and PDF reporting | All four | 2027-04-01 | 2027-05-05 | T13,T14,T15,T16 | Prediction, explanations, literature links, batch views, PDF export | Planned
T19 | End-to-end security, usability and performance tests | Mohamed + Mostafa | 2027-05-01 | 2027-05-21 | T18 | Valid/invalid input, privacy, reproducibility, browser and speed checks | Planned
T20 | Pre-final demonstration and refinements | All four | 2027-05-23 | 2027-05-27 | T19 | Working breast cancer prototype and prioritized issue fixes | Planned
T21 | Final thesis, GitHub and reproducibility audit | All four | 2027-05-28 | 2027-06-20 | T20 | Complete report, model cards, instructions, test evidence and code | Planned
T22 | Final defense preparation and demonstration | All four | 2027-06-21 | 2027-06-30 | T21 | Final demo, slide deck and Q&A; defense June 27–30 | Planned

## Gantt Chart
Project Timeline ¦ October 2026 – June 2027
■ Planned activity during the month. Tasks and dates are defined in Project Plan.
ID | Work package | Contributors | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01
T01 | Scope, requirements and risk plan | Ziad + Gamal | bar: 2026-10-01
T02 | Literature review, DOI checks and final formatting | Gamal + Ziad | bar: 2026-10-01
T03 | Dataset acquisition, labels and replicate audit | Mostafa + Mohamed | bar: 2026-10-01 to 2026-11-01
T04 | Defense I materials, repository and rehearsal | All four | bar: 2026-10-01
T05 | Expression scale, PAM50 alias and EDA verification | Mostafa + Ziad | bar: 2026-10-01 to 2026-11-01
T06 | Reproducible split and evaluation protocol | Ziad + Mohamed | bar: 2026-11-01
T07 | Initial PAM50-gene baselines | Gamal + Mostafa | bar: 2026-11-01 to 2026-12-01
T08 | Initial thesis and Defense II experiments | All four | bar: 2026-12-01
T09 | Advisor feedback and revised thesis | All four | bar: 2026-12-01
T10 | Compare PAM50 and ANOVA-selected genes | Mostafa + Gamal | bar: 2026-12-01 to 2027-02-01
T11 | Compare L1 / elastic-net-selected genes | Ziad + Mohamed | bar: 2027-01-01 to 2027-02-01
T12 | Compare LR, SVM, RF and XGBoost | All four | bar: 2027-02-01 to 2027-03-01
T13 | First Streamlit UI and input validation | Mohamed + Ziad | bar: 2027-01-01 to 2027-03-01
T14 | Curated gene biology evidence and references | Gamal + Mohamed | bar: 2027-01-01 to 2027-04-01
T15 | Select final breast model; untouched test evaluation | Ziad + Mostafa | bar: 2027-03-01
T16 | SHAP explanations and reliability checks | Gamal + Ziad | bar: 2027-03-01 to 2027-04-01
T17 | Defense III model and prototype demonstration | All four | bar: 2027-03-01
T18 | Application integration and PDF reporting | All four | bar: 2027-04-01 to 2027-05-01
T19 | End-to-end security, usability and performance tests | Mohamed + Mostafa | bar: 2027-05-01
T20 | Pre-final demonstration and refinements | All four | bar: 2027-05-01
T21 | Final thesis, GitHub and reproducibility audit | All four | bar: 2027-05-01 to 2027-06-01
T22 | Final defense preparation and demonstration | All four | bar: 2027-06-01

## Milestones
Official Milestones & Submission Evidence
Milestone | Date / window start | Evidence to present | Status
Defense I | 2026-10-27 | Project specification, literature review, Gantt, EDA evidence, GitHub, slides | Scheduled / confirm
Initial thesis | 2026-12-15 | Literature, methods and preliminary experiments | Scheduled / confirm
Defense II | 2026-12-22 | Demonstrable breast cancer modeling progress | Scheduled / confirm
Revised thesis | 2026-12-29 | Revisions based on feedback | Scheduled / confirm
Defense III | 2027-03-16 | Breast classifier results and initial explainable app | Scheduled / confirm
Pre-final defense | 2027-05-23 | Working integrated breast cancer system; window May 23–27 | Scheduled / confirm
Final thesis | 2027-06-20 | Finished documentation and reproducible code | Scheduled / confirm
Final defense | 2027-06-27 | End-to-end breast cancer demo; window June 27–30 | Scheduled / confirm

## Read Me
Guide to the Project Plan
Purpose | Defense I planning timeline through final defense; forecasts, not claims of completed work.
Project scope | Breast cancer PAM50 subtype prediction from compatible processed RNA-seq gene expression (GSE96058).
Team | Ziad Elmorsy, Mohamed Samy, Mostafa Elzeiny, Gamal Mohamed.
Collaboration | All four participate across phases; named pairings indicate practical allocation, not leadership.
Schedule editing | Update Start/Finish dates in Project Plan; Gantt cells are linked by formulas.
Submission status | Literature and combined project specification are prepared; EDA and repository need final verification.
Future work | Other cancer types and prognosis are outside the committed graduation project.
Method dependencies | Verify data → group-safe split → feature selection/model CV → held-out evaluation → SHAP → application/PDF → testing.
Dates | University schedule previously shared; confirm these dates against current official announcements.